{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":38,"n_cols":13,"rows_kept":38,"cut":false,"hidden":false,"merged":[[2,9,5,9],[2,10,5,10],[2,11,5,11],[2,12,5,12],[1,0,1,12],[2,0,5,0],[2,1,5,1],[2,2,5,2],[2,3,5,3],[2,4,5,4],[2,5,5,5],[2,6,5,6],[2,7,5,7],[2,8,5,8]],"flags":["formulas_cached_only"]}
["附件"]
["一般小（2）型病险水库除险加固项目进展情况统计表(截至2014年8月31日）"]
["省（自治区、直辖市、计划单列市）名称","签订责任书的项目\n（座）","完成初步设计批复项目\n（座）","完成招投标项目（座）","开工  项目（座）","投资下达资金\n（万元）","投资到位资金\n（万元）","投资完成资金\n（万元）","年底70% 目标项目（座）  ","主体工程完工项目（座）","全面完工项目（座）","投入使用验收或竣工验收项目（座）","竣工验收项目（座）"]
[]
[]
[]
["全  国",25040,19205,16636,16020,2307245.32,1804875.32,1685941.32,17528,13253,10822,8086,5099]
["北  京",12,12,12,12,5425.5,5425.5,5425.5,8.399999999999999,12,12,12,9]
["河  北",274,262,210,210,22651,22651,22786,191.79999999999998,120,120,81,0]
["山  西",110,103,86,81,19983,18057,16254,77,65,63,54,25]
["内蒙古",65,58,52,44,18291,18291,13275,45.5,31,27,8,8]
["辽  宁",102,99,69,69,10306,5232,3227,71.39999999999999,42,42,16,16]
["吉  林",599,403,394,394,74530,74528,60528,419.29999999999995,243,243,48,48]
["黑龙江",385,108,49,49,12630,12630,10356,269.5,21,8,1,0]
["江  苏",164,164,164,164,41848,41848,41848,114.8,164,164,164,164]
["浙  江",132,132,132,132,49400,49400,49400,92.39999999999999,132,132,110,25]
["安  徽",1000,1000,1000,958,108448,127220,118572,700,859,859,780,780]
["福  建",642,462,336,336,72930,61940,36557,449.4,280,253,163,4]
["江  西",4928,4136,3760,3532,273012,273012,223078,3449.6,2932,2765,1723,1446]
["山  东",412,379,352,332,9282,9282,9282,288.4,287,234,234,56]
["河  南",1208,1040,578,578,117931,103298,80873,845.5999999999999,486,438,107,107]
["湖  北",1514,1514,1486,1386,225000,137660,125120,1059.8,1154,878,867,623]
["湖  南",6225,2713,2022,1879,249976,71208,196118,4357.5,1444,164,223,0]
["广  东",944,944,944,944,91811,89511,67994,660.8,501,309,176,0]
["广  西",1460,1388,1044,1044,181367,181367,128542,1021.9999999999999,928,787,657,0]
["海  南",354,354,354,354,71469,71469,63870,247.79999999999998,268,196,98,0]
["重  庆",573,573,524,510,62593,62593,54062,401.09999999999997,446,420,421,170]
["四  川",1046,1046,1046,1046,68021,68021,67384,732.1999999999999,1046,988,596,399]
["贵  州",349,349,349,349,59640,59640,63885,244.29999999999998,338,294,283,39]
["云  南",2208,1635,1378,1322,397440,177430,158330,1545.6,1196,1178,1106,1068]
["陕  西",121,121,90,90,11942,11942,14600,84.69999999999999,71,65,56,10]
["甘  肃",56,56,56,56,10640,10640,13544,39.199999999999996,54,54,0,0]
["青  海",16,13,8,8,4576,4576,4429,11.2,4,4,2,2]
["宁  夏",26,26,26,26,3649,3649,4060,18.2,18,15,0,0]
["大  连",14,14,14,14,1568,1469,1469,9.799999999999999,10,9,9,9]
["宁  波",31,31,31,31,18535,18535,18722,21.7,31,31,26,26]
["厦  门",9,9,9,9,2622.5,2622.5,2622.5,6.3,9,9,9,9]
["青  岛",61,61,61,61,9728.32,9728.32,9728.32,42.699999999999996,61,61,56,56]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}